## Sheet2
No. | Task | Status | Uploader | FILENAME | Start date | End date | Notes
1 | INPUT: CSE FAK, CSE FAK FOR VELAG AND VEPBL | Completed | Jan Steven Delapaz | MRG | 2026-08-15 | 2026-08-21
1 | OUTPUT: OPUS RATES, CMDT NOTE, ORIGIN ARBS, SPECIAL NOTE | Completed | Jan Steven Delapaz | OPUS | 2026-08-15 | 2026-08-21
2 | INPUT: CSE FAK, CSE FAK FOR VELAG AND VEPBL | Completed | Jan Steven Delapaz | MRG | 2026-08-22 | 2026-08-31
2 | OUTPUT: OPUS RATES, CMDT NOTE, ORIGIN ARBS, SPECIAL NOTE | Completed | Jan Steven Delapaz | OPUS | 2026-08-22 | 2026-08-31
3 | INPUT: CSE TIER 1, CSE TIER 1 FOR VELAG AND VEPBL | In progress | Jan Steven Delapaz
3 | OUTPUT: OPUS RATES, CMDT NOTE, ORIGIN ARBS, SPECIAL NOTE | In progress | Jan Steven Delapaz
4 | INPUT: CSE TIER 1, CSE TIER 1 FOR VELAG AND VEPBL | In progress | Jan Steven Delapaz
4 | OUTPUT: OPUS RATES, CMDT NOTE, ORIGIN ARBS, SPECIAL NOTE | In progress | Jan Steven Delapaz
5 | INPUT: EAF-TZDAR | In progress | Jan Steven Delapaz
5 | OUTPUT: OPUS RATES, CMDT NOTE | In progress | Jan Steven Delapaz
6 | INPUT: EAF-TZDAR | In progress | Jan Steven Delapaz
6 | OUTPUT: OPUS RATES, CMDT NOTE | In progress | Jan Steven Delapaz
7 | INPUT: EAF-KEMBA | Completed | Jan Steven Delapaz | MRG | 2026-08-19 | 2026-08-25
7 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Jan Steven Delapaz | OPUS | 2026-08-19 | 2026-08-25
8 | INPUT: EAF-KEMBA | Completed | Jan Steven Delapaz | MRG | 2026-08-26 | 2026-09-01
8 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Jan Steven Delapaz | OPUS | 2026-08-26 | 2026-09-01
9 | INPUT: West Africa WAF | Completed | Paul Nico Cotiangco | MRG | 2026-08-26 | 2026-09-01
9 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-26 | 2026-09-01
10 | INPUT: West Africa WAF | Completed | Paul Nico Cotiangco | MRG | 2026-09-02 | 2026-09-08
10 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-09-02 | 2026-09-08
11 | INPUT: West Asia to West Africa | Completed | Paul Nico Cotiangco | MRG | 2026-08-01 | 8/14/0202
11 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-01 | 8/14/0202
12 | INPUT: West Asia to West Africa | Completed | Paul Nico Cotiangco | MRG | 2026-08-15 | 2026-08-31
12 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-15 | 2026-08-31
13 | INPUT: West Asia to WAF_SAF_EAF_MZ | Not started | Paul Nico Cotiangco
13 | OUTPUT: OPUS RATES, CMDT NOTE | Not started | Paul Nico Cotiangco
14 | INPUT: West Asia to WAF_SAF_EAF_MZ | Not started | Paul Nico Cotiangco
14 | OUTPUT: OPUS RATES, CMDT NOTE | Not started | Paul Nico Cotiangco
15 | INPUT: LAWC FAK | Completed | Paul Nico Cotiangco | MRG | 2026-08-15 | 2026-08-21
15 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-15 | 2026-08-21
16 | INPUT: LAWC FAK | Completed | Paul Nico Cotiangco | MRG | 2026-08-22 | 2026-08-31
16 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-22 | 2026-08-31
17 | INPUT: LAWC TIER 1 | Completed | Paul Nico Cotiangco | MRG | 2026-08-15 | 2026-08-21
17 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-15 | 2026-08-21
18 | INPUT: LAWC TIER 1 | Completed | Paul Nico Cotiangco | MRG | 2026-08-22 | 2026-08-31
18 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-22 | 2026-08-31
19 | INPUT: LAEC FAK | Completed | Ralfjhon Barbuena | MRG | 2026-09-01 | 2026-09-07
19 | OUTPUT: OPUS RATES, CMDT NOTE, ROUTE NOTE, ORIGIN ARBS, SPECIAL NOTE | Completed | Ralfjhon Barbuena | OPUS | 2026-09-01 | 2026-09-07
20 | INPUT: LAEC FAK | In progress | Ralfjhon Barbuena
20 | OUTPUT: OPUS RATES, CMDT NOTE, ROUTE NOTE, ORIGIN ARBS, SPECIAL NOTE | In progress | Ralfjhon Barbuena
21 | INPUT: LAEC TIER 1 | In progress | Ralfjhon Barbuena
21 | OUTPUT: OPUS RATES, CMDT NOTE, ROUTE NOTE, ORIGIN ARBS, SPECIAL NOTE | In progress | Ralfjhon Barbuena
22 | INPUT: LAEC TIER 1 | In progress | Ralfjhon Barbuena
22 | OUTPUT: OPUS RATES, CMDT NOTE, ROUTE NOTE, ORIGIN ARBS, SPECIAL NOTE | In progress | Ralfjhon Barbuena
23 | INPUT: TAD FILING AEW AMW | In progress | Ralfjhon Barbuena
23 | OUTPUT: OPUS RATES, CMDT NOTE, ROUTE NOTE, ORIGIN ARBS | In progress | Ralfjhon Barbuena
24 | INPUT: TAD FILING AEW AMW | In progress | Ralfjhon Barbuena
24 | OUTPUT: OPUS RATES, CMDT NOTE, ROUTE NOTE, ORIGIN ARBS | In progress | Ralfjhon Barbuena
25 | INPUT: TAD FILING OEW OMW | In progress | Ralfjhon Barbuena
25 | OUTPUT: OPUS RATES, CMDT NOTE, ROUTE NOTE | In progress | Ralfjhon Barbuena
26 | INPUT: TAD FILING OEW OMW | In progress | Ralfjhon Barbuena
26 | OUTPUT: OPUS RATES, CMDT NOTE, ROUTE NOTE | In progress | Ralfjhon Barbuena
27 | INPUT: TAD FILING WMW WEW | In progress | Ralfjhon Barbuena
27 | OUTPUT: OPUS RATES, CMDT NOTE, ROUTE NOTE | In progress | Ralfjhon Barbuena
28 | INPUT: TAD FILING WMW WEW | In progress | Ralfjhon Barbuena
28 | OUTPUT: OPUS RATES, CMDT NOTE, ROUTE NOTE | In progress | Ralfjhon Barbuena
29 | INPUT: AUS SEA to AUBP FAK | Completed | Symonfaith Bonagua | MRG | 2026-09-01 | 2026-09-14
29 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Symonfaith Bonagua | OPUS | 2026-09-01 | 2026-09-14
30 | INPUT: AUS SEA to AUBP FAK | Completed | Symonfaith Bonagua | MRG | 2026-08-15 | 2026-08-31
30 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Symonfaith Bonagua | OPUS | 2026-08-15 | 2026-08-31
31 | INPUT: AUS SEA to AUBP TIER 1 | Completed | Symonfaith Bonagua | MRG | 2026-09-01 | 2026-09-14
31 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Symonfaith Bonagua | OPUS | 2026-09-01 | 2026-09-14
32 | INPUT: AUS SEA to AUBP TIER 1 | Completed | Symonfaith Bonagua | MRG | 2026-08-15 | 2026-08-31
32 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Symonfaith Bonagua | OPUS | 2026-08-15 | 2026-08-31
33 | INPUT: AUS NEA to AUWC FAK | Completed | Paul Nico Cotiangco | MRG | 2026-08-15 | 2026-08-31
33 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-15 | 2026-08-31
34 | INPUT: AUS NEA to AUWC FAK | Completed | Paul Nico Cotiangco | MRG | 2026-09-01 | 2026-09-14
34 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-09-01 | 2026-09-14
35 | INPUT: AUS NEA to AUWC TIER 1 | Completed | Paul Nico Cotiangco | MRG | 2026-08-15 | 2026-08-31
35 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-15 | 2026-08-31
36 | INPUT: AUS NEA to AUWC TIER 1 | Completed | Paul Nico Cotiangco | MRG | 2026-09-01 | 2026-09-14
36 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-09-01 | 2026-09-14
37 | INPUT: AUS NEA to AUEC FAK | Not started | Riamae Zurita
37 | OUTPUT: OPUS RATES, CMDT NOTE | Not started | Riamae Zurita
38 | INPUT: AUS NEA to AUEC FAK | Not started | Riamae Zurita
38 | OUTPUT: OPUS RATES, CMDT NOTE | Not started | Riamae Zurita
39 | INPUT: AUS NEA to AUEC TIER 1 | Completed | Paul Nico Cotiangco | MRG | 2026-08-15 | 2026-08-31
39 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-15 | 2026-08-31
40 | INPUT: AUS NEA to AUEC TIER 1 | Completed | Paul Nico Cotiangco | MRG | 2026-09-01 | 2026-09-14
40 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-09-01 | 2026-09-14
41 | INPUT: NZ1 SEA to NZBP FAK | In progress | Riamae Zurita
41 | OUTPUT: OPUS RATES, CMDT NOTE | In progress | Riamae Zurita
42 | INPUT: NZ1 SEA to NZBP FAK | In progress | Riamae Zurita
42 | OUTPUT: OPUS RATES, CMDT NOTE | In progress | Riamae Zurita
43 | INPUT: NZ1 SEA to NZBP TIER 1 | Completed | Paul Nico Cotiangco | MRG | 2026-08-15 | 2026-08-31
43 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-15 | 2026-08-31
44 | INPUT: NZ1 SEA to NZBP TIER 1 | Completed | Paul Nico Cotiangco | MRG | 2026-09-01 | 2026-09-14
44 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-09-01 | 2026-09-14
45 | INPUT: NZJ NEA to NZ FAK | In progress | Riamae Zurita
45 | OUTPUT: OPUS RATES, CMDT NOTE | In progress | Riamae Zurita
46 | INPUT: NZJ NEA to NZ FAK | In progress | Riamae Zurita
46 | OUTPUT: OPUS RATES, CMDT NOTE | In progress | Riamae Zurita
47 | INPUT: NZJ NEA to NZ TIER 1 | Completed | Paul Nico Cotiangco | MRG | 2026-08-15 | 2026-08-31
47 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-08-15 | 2026-08-31
48 | INPUT: NZJ NEA to NZ TIER 1 | Completed | Paul Nico Cotiangco | MRG | 2026-09-01 | 2026-09-14
48 | OUTPUT: OPUS RATES, CMDT NOTE | Completed | Paul Nico Cotiangco | OPUS | 2026-09-01 | 2026-09-14
49 | INPUT: LAEC LUX | Not started | Riamae Zurita
49 | OUTPUT: OPUS RATES, CMDT NOTE | Not started | Riamae Zurita
50 | INPUT: LAEC LUX | Not started | Riamae Zurita
50 | OUTPUT: OPUS RATES, CMDT NOTE | Not started | Riamae Zurita
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started